## Observations
|  | Dev | Test
Below are the issues noticed during the TCL deployment and verificaton. Some are already fixed, some of them needs fix and tests.
Every policy executes should be part of policy studio. Even the default rules should appear in read-only if needed. | Rajareddy | Complete | Complete
Policy Binding: Remove tools and mcp servers | Rajareddy | Complete | Complete
Policy Binding: Bind policy to the latest DID only | Rajareddy | Complete | Complete
Policy Binding: Fix Effective Policy preview page to load with accurate data and evaluate correctly. | Rajareddy | TODO
UI/Backend: Should always use latest DID+active, all other DIDs to stay as historical data | Mallaiah | Complete | Complete
Agent Registry: Have a simple search bar to quickly locate Agents | Mallaiah | Complete | Complete
Agent Name should not repeat in the table for each (Bootstrap) DID created. | Mallaiah | Complete | Complete
Bootstrap: Contain bootstrap token requirement for each restart | Mallaiah | Complete | In-Progress
Bootstrap: Create store agent keys securely per DID to survive restarts | Mallaiah | Complete | In-Progress
Sponsor: Should be able to remove angets from Sponsors or reassign to other sponsor | Rajareddy | Complete | Complete | Reassingn = requires (admin,super admin) privileges
Sponsor: Revoke agents individually from Sponsor's agent table | Rajareddy | Complete | Complete | we can only revoke (no remove, yet to implement)
SDK: Reduce the number of environment variables and consolidate them into essentials with other having correct defaults | Rajareddy | Complete phase-1 | In-Progress
SDK: Fix mesh code to have wrappers to reduce the edited code on Agent side | Mallaiah | TODO
SDK: Scripts to build wheels for both linux and win32 platforms | Mallaiah | Complete | Complete
SDK: A2A initiator gate — @peer_verified + kernel.a2a_gate | Mallaiah | Completre | In-Progress
Governance Gap: Policy Bindings Break When an Agent Re-registers | Mallaiah | Complete | TODO
Policy: Auto trigger policies upon Risk Score thresholds | Praveen | Complete | In-Progress

## Test-Env
Section | Item | Value / Command | Why it matters | Notes
Scope | Feature set under test | Bootstrap retirement: durable agent credential + private-key escrow, plus IMPL-065 peer resolution and agent counting | An operator registers an agent once; the agent escrows its private key; every restart recovers the same key and keeps the SAME DID instead of consuming a bootstrap token and resetting trust history
Scope | PRs covered | core #69 #70 #73 #74 #75 #76 #77 #78; ui-user #28 #29; sdk #20 #21 | All were open at time of writing. Merge order matters - see row below
Scope | Merge order | core #69 - #70 - #75 - #77 - #78 - #76 then sdk #21; ui-user #28 - #29 | core #76 MUST merge before sdk #21: P3 imports agentmesh.identity.key_backup and its escrow tests SKIP (not fail) without it, so CI looks green while agents mint a new DID per restart
Scope | Out of scope | core #51 (targets main, CONFLICTING since 2026-07-15) | Not part of this milestone
Stack | Front door (browser origin) | http://localhost:20350/aisec-agents-gov-ui/ | Same-origin edge. The SPA calls /aisec-agents-gov/api/v1/* and the edge strips the prefix
Stack | Entry URL (REQUIRED) | http://localhost:20350/aisec-agents-gov-ui/auth/handoff?token=dev&orgCode=demodevelop&redirect=/overview | Opening the SPA root instead shows 'No active session'. AuthGuard bounces to the platform-login sentinel, which 302s to :4200 (not part of this stack), then shows a terminal notice | Most common tester mistake
Stack | orgCode value | Must match the org the dev user is bound to (demodevelop by default) | platform:dev-user is bound to demodevelop in seeded data. Using orgCode=default returns 403 'URL org code does not match the authenticated tenant' | Second most common mistake
Stack | Edge container | agt-dev-edge on :20350 | Injects X-Auth-Info only when X-Auth-Token is present; scripts/dev-edge.sh up
Stack | UI container | agt-ui on :20351, image aisec-agents-gov-ui-user:local
Stack | CP API | pgai-core on :20355
Stack | Postgres | pgai-db on 127.0.0.1:5433
Build | UI image build - CRITICAL | docker build -f docker/aisec-agents-gov-ui-user/service.Dockerfile --build-arg APP_BACKEND_URL= -t aisec-agents-gov-ui-user:local . | Building via docker-compose bakes a REMOTE backend. The compose default is ${APP_BACKEND_URL:-https://api.sqa1.appsoc.com} and :- substitutes the default for EMPTY as well as unset, so the SPA calls a remote host. Build outside compose | Verified defect. See TC-ENV-004
Build | Verify the UI build before testing | Extract /usr/share/nginx/html from the image and grep for appsoc.com - expect 0 matches, and grep for /aisec-agents-gov/api/v1 - expect present | Confirms a relative same-origin API base was baked
Build | BuildKit | Set DOCKER_BUILDKIT=0 | BuildKit is broken on the reference machine (driver not connecting)
Build | Frontend deps | npm install --legacy-peer-deps | Plain npm ci FAILS with ERESOLVE: openapi-typescript@7.4.1 wants typescript@^5.x, lockfile pins 5.9.3. Pre-existing, unrelated to these changes
Build | Backend test path | cd control-plane/backend; pytest tests/ -q
Build | agent-mesh test path | PYTHONPATH=packages/agent-mesh/src pytest packages/agent-mesh/tests -q | WITHOUT the PYTHONPATH override the new test modules fail COLLECTION (No module named agentmesh.identity.key_backup) because an installed agentmesh shadows the checkout. Reads as broken code rather than mis-pathed
Build | SDK test path | PYTHONPATH=<sdk>/agent-os-sdk/src:<core>/packages/agent-mesh/src pytest tests/ -q | Same shadowing issue
Data | Postgres volume - CRITICAL | Use a FRESH volume, or a SECRET_KEY matching the one that wrote the existing data | Reusing an old dev volume gives 'CP Root DID bootstrap failed: Secret decryption failed: InvalidTag'. This is a config/data mismatch, NOT an IMPL-020 defect - the legacy read path works, the key simply differs | See TC-ENV-002
Data | Test data age | Agents created before this feature show live_credential_count=0 and key_escrowed=false | They predate the flow, so they render as 'not enrolled'. The UI will look unchanged unless you register a NEW agent and start it once | Explains 'I see no UI change'
Data | IMPL-066 liveness sweep | Idle fleets get epochs revoked over time | On a stack left running ~1.5h with nothing heartbeating, did_status shifted from superseded 131 / active 35 to revoked 160 / active 7. Counts are a moving target - re-read immediately before asserting | Affects any count-based assertion
Credentials | Org-wide passphrase | AGT_AGENT_PASSPHRASE - min 32 chars | Host-local, organisation-wide, ENCRYPTION ONLY. Never authenticates, never sent to the CP
Credentials | Agent credential | AGT_AGENT_TOKEN | NEW variable. AGT_CP_TOKEN remains for operator/service tokens. Flow triggers if EITHER is set, then REQUIRES both
Credentials | Never use | agt-prod-pg | Has NO docker volume - docker rm destroys demo data irrecoverably. Also exists in TWO docker engines under the same name on the reference machine; check which engine before any action
Exit | Definition of done | All P1 cases Pass; no P1/P2 Fail; every Blocked case has an owner

## Test-Cases
TC ID | Area | Feature | IMPL / PR | Title | Type | Priority | Preconditions | Steps | Expected Result | Verify Via | Existing Auto Coverage | QA Result | Tested By | Date | Comments
TC-ENV-001 | Environment | Stack brings up clean | all | Full stack starts and all services report healthy | Smoke | P1 | Fresh Postgres volume | 1) Bring up pgai-db, pgai-core, agt-ui, agt-dev-edge; 2) docker ps | All 4 containers Up; pgai-db and redis report healthy | CLI | none
TC-ENV-002 | Environment | Alembic from scratch | #70 #75 #77 | Migration chain builds from an empty database | Smoke | P1 | EMPTY Postgres volume, agents_gov schema created | 1) Start pgai-core against an empty DB; 2) Read startup logs | Chain runs 0001 to 0030 including 0028 - 0029 - 0030 in that order; single head; 'CP Root DID generated and persisted'; NO InvalidTag | CP log | partial
TC-ENV-003 | Environment | Single alembic head | #70 #75 | Merged branches leave exactly one alembic head | Regression | P1 | Both #70 and #75 merged | 1) alembic heads | Exactly one head: 0030_logical_agent_trust_ceiling | CLI | none |  |  |  | 0029 must be rechained onto 0028; both were cut from staging-main and chain to 0027, giving TWO heads if unfixed. Must NOT be papered over with alembic merge
TC-ENV-004 | Environment | No remote backend baked into the SPA | ui #28 #29 | UI image calls the local CP, never a remote host | Security | P1 | UI image built | 1) Extract /usr/share/nginx/html from the image; 2) grep -r appsoc.com; 3) grep -r /aisec-agents-gov/api/v1; 4) Load the SPA and watch the browser Network tab | grep for appsoc.com returns 0; relative API base present; every XHR goes to localhost:20350 | Image + browser devtools | none |  |  |  | Confirmed defect path: building via docker-compose bakes https://api.sqa1.appsoc.com. Never test against an image built with plain compose
TC-ENV-005 | Environment | Handoff is the entry point | ui | SPA authenticates via the handoff URL | Smoke | P1 | Stack up | 1) Open the handoff URL with token=dev and orgCode=demodevelop | Lands on /overview, authenticated; no 'No active session' | UI | none
TC-ENV-006 | Environment | SPA root shows a terminal notice, not a loop | ui | Opening the SPA root does not redirect-loop | Negative | P2 | Stack up, no session in localStorage | 1) Open http://localhost:20350/aisec-agents-gov-ui/ directly | Shows 'No active session' once. Does NOT loop between the sentinel and the app | UI | none
TC-ENV-007 | Environment | Wrong orgCode is rejected clearly | CP | Tenant mismatch returns an actionable 403 | Negative | P2 | Dev user bound to demodevelop | 1) Call the API with orgCode=default in the URL | 403 with detail 'URL org code does not match the authenticated tenant' | API | none
TC-HKDF-001 | Secrets at rest | HKDF-SHA256 derivation | IMPL-020 P1 / #69 | New secrets are written in v2 format | Functional | P1 | Fresh DB | 1) Start the CP so a root DID is generated; 2) SELECT left(private_key_enc,3) FROM system_keys | Prefix is 'v2:' (v2:salt:iv:ct) | DB | yes - test_encryption_hkdf.py
TC-HKDF-002 | Secrets at rest | Legacy blobs still readable | IMPL-020 P1 / #69 | Pre-HKDF secrets decrypt after upgrade | Regression | P1 | A DB whose root key was written BEFORE Phase 1, with the SAME SECRET_KEY | 1) Start the upgraded CP against it; 2) Read startup logs | CP Root DID loaded from system_keys'; no InvalidTag; blob prefix is NOT v2: | CP log + DB | yes - test_pre_hkdf_blob_still_decrypts |  |  |  | THE critical upgrade case. A strict cutover would kill the bootstrap flow on first restart, before an operator could reach any migration endpoint
TC-HKDF-003 | Secrets at rest | Wrong SECRET_KEY fails closed | IMPL-020 P1 / #69 | A mismatched key does not silently succeed | Negative | P2 | DB written under key A | 1) Start the CP with key B | Startup logs 'Secret decryption failed: InvalidTag' and continues; does not fabricate a new root DID silently over the old one | CP log | none |  |  |  | Distinguish from TC-HKDF-002: same message, opposite cause. Confirm the SECRET_KEY before filing a bug
TC-HKDF-004 | Secrets at rest | Rollback is a one-way door | IMPL-020 P1 / #69 | Pre-Phase-1 code cannot read v2 blobs | Negative | P3 | A DB containing v2 blobs | 1) Run pre-Phase-1 code against it | Fails to decrypt | CP log | none |  |  |  | Release-note item, not a bug. Rollback after any v2 write is unsafe
TC-BSN-001 | Bootstrap name binding | Token bound to one name | IMPL-067 P1 / #70 | A bootstrap token can only claim its own agent name | Security | P1 | Bootstrap flow still enabled | 1) Mint a bootstrap token for agent A; 2) Attempt to consume it declaring agent name B | Refused | API | yes - test_bootstrap_name_binding.py |  |  |  | Closes a live spoofing hole: BootstrapTokenCreate previously carried no agent name, so ANY valid token could claim ANY agent
TC-BSN-002 | Bootstrap name binding | Correct name still works | IMPL-067 P1 / #70 | Name binding does not break the legacy path | Regression | P1 | Bootstrap flow enabled | 1) Mint a token for agent A; 2) Consume it declaring A | Succeeds | API | yes
TC-BSN-003 | Bootstrap name binding | Legacy path emits a deprecation warning | IMPL-067 P3 / sdk #21 | Bootstrap use is signposted as legacy | Functional | P3 | Agent configured with AGT_BOOTSTRAP_TOKEN only | 1) Start the agent | Works, and logs a deprecation warning | Agent log | yes
TC-REG-001 | Register Agent | Provision returns a credential once | IMPL-067 P2 / #77 | Operator registration mints a durable credential | Functional | P1 | Operator session | 1) POST /orgs/{org}/agents/provision with name, agent_type, trust_ceiling | 201; response carries logical_agent_id, credential, credential_id, expires_at, trust_ceiling, cp_root_did, already_existed=false | API | yes - test_agent_registration_credential.py
TC-REG-002 | Register Agent | Credential TTL is one year and does not slide | IMPL-067 P2 / #77 | IMPL-066 liveness does not expire agent credentials | Functional | P1 | Agent registered | 1) Note expires_at; 2) Start the agent; 3) Re-read the credential expiry | expires_at is ~1 year out and is UNCHANGED after agent activity | API + DB | yes - test_registration_credential_does_not_slide |  |  |  | Without this, IMPL-066's 15-minute window would lapse every agent 15 min after it stops. Currently correct only because renewed_expiry never shortens - the test pins it
TC-REG-003 | Register Agent | Route is /provision not /register | IMPL-067 P2 / #77 | The new route does not shadow wire-1.0 mesh registration | Regression | P1 | Stack up | 1) POST /agents/provision; 2) POST /agents/register | Both resolve to their own handlers; mesh registration still works | API | yes |  |  |  | handshake.py already owns POST /agents/register and the new router mounts FIRST, so reusing the path would silently shadow it
TC-REG-004 | Register Agent | Re-registering an existing name is flagged | IMPL-067 P2 / #77 | already_existed tells the operator the old credential is still live | Functional | P2 | Agent already registered | 1) POST /provision again with the same name | already_existed=true; the previous credential remains valid | API + UI | yes |  |  |  | Leaving two valid credentials silently is how one stays valid for a year
TC-REG-005 | Register Agent | Request body has no name-spoofing field | IMPL-067 P2 / #77 | The handler cannot read an agent name from the body | Security | P2 | Operator session | 1) POST /provision with an extra unexpected field in the body | Extra field ignored (pydantic drops unknowns); no behaviour change | API | yes - test_the_request_body_has_no_name_field
TC-REG-006 | Register Agent | UI: Register Agent shows the credential once | ui #28 | CredentialReveal displays the secret exactly once | Functional | P1 | Logged into the UI | 1) Agent Registry - Register Agent; 2) Fill name, type, trust ceiling; 3) Submit; 4) Dismiss and revisit | Credential shown once with a copy affordance and a 'shown once' warning; NOT retrievable after dismissal | UI | none - repo has NO test framework
TC-REG-007 | Register Agent | UI: sponsor and capabilities are not asked for | ui #28 | Form collects only what is true at registration | Functional | P3 | UI open | 1) Open the Register Agent form | No sponsor_email or capabilities fields; trust_ceiling and ttl_days present; blank ttl_days omitted from the request | UI + network tab | none |  |  |  | Sponsor is read from the operator session; capabilities are declared by the agent at attach, where they are true rather than aspirational
TC-REG-008 | Register Agent | UI: legacy bootstrap panel is labelled | ui #28 | Bootstrap UI is marked Legacy | Functional | P3 | UI open | 1) Open Agent Registry | Bootstrap token panel present and visibly marked Legacy | UI | none
TC-IDENT-001 | Identity attach | First boot generates and attaches a DID | IMPL-067 P3 / sdk #21 | Agent self-generates its keypair | Functional | P1 | Registered agent; AGT_AGENT_TOKEN and AGT_AGENT_PASSPHRASE set | 1) Start the agent once | Attach succeeds; DID = did:mesh:<24 hex>; new_epoch=true; agent appears in the registry | Agent log + API | yes - test_agent_credential.py
TC-IDENT-002 | Identity attach | Private key never leaves the agent | IMPL-020 / #75 #76 | CP never receives plaintext key material | Security | P1 | Agent started once | 1) Inspect the escrow row; 2) Inspect CP logs and the attach request body | Only a public key and ciphertext are transmitted; no private key in any request or log | DB + CP log + capture | yes
TC-IDENT-003 | Identity attach | Sponsorship VC is signed at attach | IMPL-067 P2 / #77 | VC commits to a key that exists | Functional | P2 | Registered agent | 1) Start the agent; 2) Inspect the attach response | sponsorship_credential returned at ATTACH, not at registration; operator recorded on the credential is reflected | API | yes |  |  |  | Spec D4 said registration issues it; not buildable - the VC subject is the DID and its body carries the public key, neither of which exists until first boot
TC-ESC-001 | Key escrow | Restart recovers the SAME DID | IMPL-020 P2 P3 + IMPL-067 P3 | The core promise of the feature | Functional | P1 | Agent started once (key escrowed) | 1) Run the agent 3 times in 3 SEPARATE OS processes with the same token and passphrase | Identical DID all 3 times; new_epoch=false on runs 2 and 3; epoch_count stays 1 | Agent log + API + DB | yes |  |  |  | Separate processes matter: nothing can be carried in memory, so a stable DID proves recovery from escrow
TC-ESC-002 | Key escrow | Exactly one current escrow row | IMPL-020 P2 / #75 | Restarts do not accumulate escrow rows | Functional | P1 | Agent started 3 times | 1) SELECT count(*) FROM agent_key_escrow WHERE superseded_by IS NULL | Exactly 1 | DB | yes
TC-ESC-003 | Key escrow | Escrow is written on first boot only | IMPL-067 P3 / sdk #21 | No rewrite on every restart | Functional | P2 | Agent started once | 1) Note key_escrowed_at; 2) Restart the agent; 3) Re-read key_escrowed_at | Timestamp UNCHANGED | API | yes
TC-ESC-004 | Key escrow | Wrong passphrase fails CLOSED | IMPL-067 P3 / sdk #21 | A bad passphrase must not mint a new identity | Security | P1 | Agent with an escrowed key | 1) Start the agent with a different AGT_AGENT_PASSPHRASE | Raises KeyRecoveryFailed (InvalidTag). Agent does NOT start, does NOT mint a new DID, and the escrow row is NOT overwritten | Agent log + DB | yes |  |  |  | KeyRecoveryFailed is a separate class specifically so fail_mode=open cannot reach it. fail_mode=open means 'run ungoverned', never 'run as a different agent'
TC-ESC-005 | Key escrow | fail_mode=open does not bypass key recovery | IMPL-067 P3 / sdk #21 | Fail-open never means fail-into-a-new-identity | Security | P1 | Agent with an escrowed key | 1) Set fail_mode=open; 2) Start with the wrong passphrase | Still fails closed with KeyRecoveryFailed | Agent log | yes
TC-ESC-006 | Key escrow | Escrow WRITE failure is fail-open | IMPL-067 P3 / sdk #21 | A failed backup must not kill the agent | Functional | P2 | Registered agent; escrow endpoint made unreachable | 1) First boot with the escrow PUT failing | Agent starts and runs; logs a loud warning naming the cost (next restart mints a new DID) | Agent log | yes |  |  |  | Asymmetry is deliberate: a failed backup costs the next restart; a failed startup costs the agent entirely
TC-ESC-007 | Key escrow | An agent cannot read another agent's blob | IMPL-020 P2 / #75 | Escrow GET takes no name and no DID | Security | P1 | Two agents in the same org, both escrowed | 1) As agent A, attempt to fetch agent B's blob by any means | Impossible to express - GET returns only the caller's own blob; no name or did parameter exists | API | yes |  |  |  | The property holds by construction. Spec says explicitly NOT to add a parameter later for symmetry with PUT
TC-ESC-008 | Key escrow | Write is name-bound too | IMPL-020 P2 / #75 | A token for A cannot write under B's name | Security | P1 | Two registered agents | 1) As agent A, PUT an escrow blob declaring agent name B | Refused | API | yes |  |  |  | A token for A writing under B's name is a denial of service on B's identity even though it cannot read it
TC-ESC-009 | Key escrow | Unbound credential is denied | IMPL-020 P2 / #75 | Absence of a binding row is a denial | Security | P1 | An operator or service token (not an agent credential) | 1) Call the escrow endpoints with it | Refused | API | yes |  |  |  | Binding lives in agent_credential_bindings, deliberately NOT a nullable api_tokens.agent_id - a nullable column would inherit a NULL-matches-any predicate and open every operator token onto every agent's blob
TC-ESC-010 | Key escrow | Ambiguous (org,name) is refused, not guessed | IMPL-020 P2 / #75 | Duplicate logical names 409 rather than pick one | Negative | P2 | Two logical agents resolvable to the same (org,name) | 1) Attempt escrow resolution | 409 conflict; never a silent choice | API | yes
TC-ESC-011 | Key escrow | Escrow is keyed on (org,name), not the credential | IMPL-020 P2 / #75 | Rotating the credential preserves the identity | Functional | P1 | Agent escrowed and running | 1) Rotate the credential; 2) Start the agent with the NEW credential | SAME DID recovered | API + agent log | yes |  |  |  | Sharpest confirmation that escrow is keyed on the logical agent: the credential changed and the identity did not
TC-ESC-012 | Key escrow | Cross-tenant escrow isolation | IMPL-020 P2 / #75 | An org cannot reach another org's escrow | Security | P1 | Two orgs, each with an escrowed agent | 1) Use org A's agent credential against org B's escrow routes | Refused | API | yes
TC-GUARD-001 | Rotation guard | backup refuses a key that does not match the DID | IMPL-020 P3 / #76 | Escrowing a rotated key would replace the identity | Security | P2 | agent-mesh available | 1) Call backup(expected_did=<other DID>) with a non-matching key | Returns False, logs an ERROR, and leaves the PREVIOUS blob current | Unit test + log | yes - test_key_backup.py |  |  |  | A DID IS sha256(public_key)[:24]. Storing a non-matching key is strictly worse than storing nothing: the next restart would derive an unknown identity, open a new epoch, and present as a clean start
TC-GUARD-002 | Rotation guard | Rotation never writes to escrow | IMPL-020 P3 / #76 | The identity key never rotates | Security | P2 | Source checkout | 1) grep rotation.py for backup/escrow/KeyBackupService references | Zero references. KeyRotationManager rotates SIGNING keys only | Code review | yes |  |  |  | Decision 2026-07-30: the identity key is generated once at enrolment and replaced only by re-enrolling. Escrow is written at exactly two moments - first boot and re-enrolment - and neither is a rotation
TC-TIER-001 | Keystore tiers | Escrow tier is selected by default | IMPL-020 P3 / #76 | Auto-probe falls through to escrow | Functional | P2 | Host with no HSM/KMS/TPM | 1) Resolve the keystore tier | Tier 4 (escrow) selected; agent starts | Unit test + agent log | yes - test_keystore_tier.py
TC-TIER-002 | Keystore tiers | Auto-probe never selects an unimplemented tier | IMPL-020 P3 / #76 | A PKCS#11 library must not take down a fleet | Negative | P1 | Host WITH a PKCS#11 library present | 1) Start the agent with no tier lock | Still resolves to escrow and starts. Does NOT auto-select tier 1 and refuse to boot | Unit test | yes |  |  |  | DELIBERATE deviation from spec §3.7's literal wording - flag to reviewers. Taken literally, installing a library would break a working fleet
TC-TIER-003 | Keystore tiers | An operator lock is a lock | IMPL-020 P3 / #76 | A pinned tier refuses rather than downgrades | Negative | P1 | Host with no KMS | 1) Set AGT_KEYSTORE_TIER=kms; 2) Start the agent | REFUSES to start with an actionable error. Does NOT silently fall back to escrow | Unit test + agent log | yes |  |  |  | Silently giving a weaker tier is worse than not starting, because it looks like it worked
TC-TIER-004 | Keystore tiers | A recorded tier is sticky | IMPL-020 P3 / #76 | Losing hardware refuses rather than re-resolving down | Negative | P2 | Agent previously resolved to a hardware tier | 1) Remove the hardware; 2) Restart the agent | REFUSES, and the error says deleting the state file is the deliberate re-enrol | Unit test + agent log | yes |  |  |  | Coming up on a weaker tier means generating a new identity and calling it a clean start
TC-VIS-001 | Escrow visibility | Enrolment endpoint returns both facts | #78 | Operator can see whether an agent survives a restart | Functional | P1 | Registered agent | 1) GET /orgs/{org}/agents/{logical_agent_id}/enrolment | 200 with live_credential_count, credential_expires_at, credential_issued_at, key_escrowed, key_id, key_escrowed_at, kdf, epoch_count | API | yes - 9 new tests
TC-VIS-002 | Escrow visibility | Never returns ciphertext | #78 | Key material stays out of an operator response | Security | P1 | Agent with an escrowed key | 1) GET the enrolment endpoint; 2) Search the response body for the ciphertext | Ciphertext absent | API | yes - asserted by test |  |  |  | An operator holds the credential but not the passphrase; handing them ciphertext moves key material somewhere it has no reason to be
TC-VIS-003 | Escrow visibility | Reports the CURRENT escrow row | #78 | Superseded blobs are not reported as current | Functional | P2 | Agent with a superseded and a current escrow row | 1) GET the enrolment endpoint | Reflects the blob a restart would actually recover (superseded_by IS NULL), not merely the newest | API + DB | yes
TC-VIS-004 | Escrow visibility | Operator route rejects an agent credential | #78 | Agent tokens cannot read operator views | Security | P1 | An agent credential | 1) Call the enrolment endpoint with it | Refused | API | yes
TC-VIS-005 | Escrow visibility | Cross-tenant enrolment isolation | #78 | Another org's operator cannot read this agent | Security | P1 | Two orgs | 1) Call org A's enrolment endpoint as org B's operator | Refused | API | yes
TC-VIS-006 | Escrow visibility | State: survives | ui #29 + #78 | Live credential + escrowed key | Functional | P1 | Agent registered AND started once | 1) Open Agent Detail | Shows it keeps its DID, trust score, drift history and policy bindings across a restart | UI | none |  |  |  | To produce this state you MUST register a new agent and start it once - pre-existing agents will not show it
TC-VIS-007 | Escrow visibility | State: awaiting first start | ui #29 + #78 | Registered, not yet started | Functional | P1 | Agent registered, never started | 1) Open Agent Detail | Shows 'waiting for its first start' as a BENIGN state, not a warning | UI | none |  |  |  | Exists because the 4-state version cried wolf: a fresh registration and a running agent whose escrow failed report the SAME two facts and mean opposite things. epoch_count separates them
TC-VIS-008 | Escrow visibility | State: NEW DID on restart | ui #29 + #78 | Has an identity, nothing escrowed | Functional | P1 | Agent with an identity but escrow suppressed/failed | 1) Open Agent Detail | Prominent warning that it runs fine today and silently replaces itself on its next restart | UI | none |  |  |  | THE state this feature exists for - invisible on every other screen
TC-VIS-009 | Escrow visibility | State: stopped, recoverable | ui #29 + #78 | No live credential, key intact | Functional | P2 | Agent escrowed, then credential revoked | 1) Open Agent Detail | Shows it cannot start but its identity is intact and re-registering the same name restores it | UI | none
TC-VIS-010 | Escrow visibility | State: not enrolled | ui #29 + #78 | Neither credential nor key | Functional | P2 | A pre-feature agent | 1) Open Agent Detail | Shows not enrolled | UI | none |  |  |  | This is what ALL pre-existing agents show - expect the page to look unchanged for them
TC-VIS-011 | Escrow visibility | Escrowed key DID mismatch is surfaced | ui #29 | A superseded-epoch blob is visible as such | Functional | P3 | Escrowed key whose DID differs from the current DID | 1) Open Agent Detail | Escrowed key DID shown; mismatch indicated | UI | none
TC-VIS-012 | Escrow visibility | Multiple live credentials are called out | ui #29 | Wider blast radius than a bare count implies | Functional | P2 | Agent re-registered so 2 credentials are live | 1) Open Agent Detail | A note explains more than one credential can authenticate as this agent and that rotation reduces it to one | UI | none
TC-VIS-013 | Escrow visibility | Status refreshes after rotate and revoke | ui #29 | No stale assessment above the action | Functional | P1 | Agent Detail open | 1) Rotate; 2) Observe the panel; 3) Revoke; 4) Observe again | Status query is invalidated and re-fetched each time; never shows a pre-action assessment | UI | none |  |  |  | The one place in this panel where a stale read actively misleads
TC-ROT-001 | Rotate / revoke | Rotate issues one and revokes the rest | IMPL-067 P2 / #77 | Rotation converges to a single credential | Functional | P1 | Agent with a live credential | 1) POST /agents/{id}/credential/rotate | New credential returned; revoked_count reflects the old ones; the NEW credential is spared | API | yes |  |  |  | Mutation testing found keep_token_id was inert because the binding row was not flushed - sparing the new credential rested on flush ordering
TC-ROT-002 | Rotate / revoke | Old credential is refused after rotation | IMPL-067 P2 / #77 | Rotation actually invalidates | Security | P1 | Credential rotated | 1) Start the agent with the OLD credential | Refused with 401 | Agent log | yes
TC-ROT-003 | Rotate / revoke | Revoke stops the agent | IMPL-067 P2 / #77 | Revocation is immediate | Functional | P1 | Agent running with a credential | 1) DELETE /agents/{id}/credential; 2) Start the agent | revoked_count returned; agent refused immediately | API + agent log | yes
TC-ROT-004 | Rotate / revoke | Revoke PRESERVES the escrowed key | IMPL-067 / #77 #78 | Revoke is a stop button, not a delete button | Functional | P1 | Agent escrowed, then revoked | 1) Check the enrolment endpoint after revoke | key_escrowed stays TRUE; live_credential_count=0 | API + DB | yes |  |  |  | Found in a live run: the UI dialog had claimed re-registration mints a new DID. It does not - a destructive confirm that overstates permanence is the wrong way round
TC-ROT-005 | Rotate / revoke | Re-registering after revoke restores the SAME DID | IMPL-067 / #77 | Revocation is reversible | Functional | P1 | Agent escrowed then revoked | 1) POST /provision with the SAME name; 2) Start the agent | already_existed=true and the SAME DID returns, with history intact | API + agent log | yes
TC-ROT-006 | Rotate / revoke | UI revoke dialog states reversibility correctly | ui #29 / 729e6fd | Copy must not overstate permanence | Functional | P2 | Agent Detail open | 1) Open the revoke confirmation | States the escrowed key survives and re-registering the same name restores the same DID. Does NOT claim a new DID is minted | UI | none |  |  |  | No unit test can catch this - the claim is about the CP's storage model, which the UI only describes
TC-ERR-001 | Error messages | Rejected credential blames the credential | sdk f0b2553 | Do not send operators to check a healthy passphrase | Functional | P1 | Revoked or rotated-away credential | 1) Start the agent with it | Error names AGT_AGENT_TOKEN explicitly, says 'This is the credential, not the passphrase', and mentions revoked/rotated/not-an-agent-credential | Agent log | yes |  |  |  | Escrow fetch is the FIRST call the credential makes, so all three causes surfaced as 'could not fetch the escrowed key (HTTP 401)'
TC-ERR-002 | Error messages | Missing passphrase is actionable | IMPL-067 P3 / sdk #21 | Half-configured must not fall back silently | Negative | P1 | AGT_AGENT_TOKEN set, AGT_AGENT_PASSPHRASE unset | 1) Start the agent | Actionable error naming the missing variable. Does NOT fall back to the legacy path and re-identify | Agent log | yes |  |  |  | Flow triggers if EITHER variable is set, then requires BOTH. Gating on the passphrase alone would let 'token set, passphrase forgotten' silently re-identify every restart
TC-ERR-003 | Error messages | Short passphrase refused at construction | IMPL-020 P3 / #76 | HKDF stretches, it does not create entropy | Negative | P2 | Passphrase under 32 chars | 1) Start the agent | Refused in the constructor with a clear message | Agent log | yes
TC-ERR-004 | Error messages | agent-mesh missing is explained | IMPL-067 P3 / sdk #21 | Escrow unavailable must be loud | Negative | P2 | agent-mesh NOT installed | 1) First boot | Agent runs; warns that escrow is UNAVAILABLE and the next restart will mint a NEW DID | Agent log | yes |  |  |  | If core #76 has not merged, escrow tests SKIP rather than fail - CI looks green while every restart re-identifies
TC-CNT-001 | Agent counting | Summary counts agents, not epochs | IMPL-065 / #73 | Restarts do not inflate the total | Functional | P1 | An agent with several epochs | 1) GET /agents/summary | total counts the AGENT once regardless of epoch count | API | yes - test_agents_summary_logical.py |  |  |  | On real data this changed 167 to 35: 160 live epochs across 28 agents plus 7 unclaimed rows
TC-CNT-002 | Agent counting | A live unsuperseded epoch does not double-count | IMPL-065 / #73 | The case the retired-filter could not catch | Functional | P1 | Agent with an old epoch still marked active | 1) GET /agents/summary | Counted once | API | yes
TC-CNT-003 | Agent counting | Governed agent with no logical row still counts | IMPL-065 / #73 | Do not drop wire-1.0 / POST /agents arrivals | Regression | P1 | An Agent row with has_identity=true and no logical_agent_id | 1) GET /agents/summary | Counted as one agent | API + DB | yes |  |  |  | NONE of the five Agent-creating paths set logical_agent_id, and two set has_identity=true. Counting only LogicalAgent rows would silently drop them
TC-CNT-004 | Agent counting | Registered-but-never-started still counts | IMPL-065 / #73 | Do not drop agents awaiting first boot | Regression | P1 | Logical agent with no epoch | 1) GET /agents/summary | Counted in total; contributes to NO status bucket | API | yes |  |  |  | Registration creates the logical row; the first epoch appears at attach. In between the agent exists and holds a credential
TC-CNT-005 | Agent counting | shadow_count is a SUBSET of total | IMPL-065 / #73 | Total and Shadow must describe one population | Functional | P2 | Org with governed and shadow agents | 1) GET /agents/summary | shadow_count < total; shadow agents are included in total | API | yes |  |  |  | Previously disjoint sets presented as though one contained the other
TC-CNT-006 | Agent counting | Status buckets follow the current epoch | IMPL-065 / #73 | Summary and listing must agree on an agent's state | Functional | P2 | Agent whose current epoch differs in status from a newer row | 1) GET /agents/summary; 2) GET /agents?view=logical | Buckets reflect LogicalAgent.current_agent_id, matching the listing's current_status | API | yes
TC-CNT-007 | Agent counting | Overview and Agent Registry agree | IMPL-065 / #73 + ui | The user-visible symptom | Functional | P1 | Both pages reachable; CP rebuilt with the fix | 1) Read Total on Overview; 2) Read Total on Agent Registry; 3) Reload with a partially paginated registry | Both show the SAME number, and it does not change with pagination state | UI | none |  |  |  | Root cause was two units: the clients preferred a logical count once fully paginated and fell back to a DID-based total otherwise
TC-CNT-008 | Agent counting | Retired epochs excluded | IMPL-066 / #73 | Churn is not fleet size | Regression | P2 | Agent with superseded epochs | 1) GET /agents/summary | Superseded epochs excluded | API | yes - test_epoch_retention.py |  |  |  | This test passes UNMODIFIED after the counting fix - a signal the new definition is right
TC-CNT-009 | Agent counting | Summary is tenant-scoped | IMPL-065 / #73 | No cross-tenant counting | Security | P1 | Two orgs with agents | 1) GET /agents/summary as org A | Counts only org A | API | yes
TC-CNT-010 | Agent counting | Naive datetime does not crash the summary | IMPL-065 / #73 | Latent TypeError on credential expiry | Regression | P3 | credential_expires_at populated; driver returning naive datetimes | 1) GET /agents/summary | 200, no TypeError | API | yes |  |  |  | Pre-existing latent bug: Postgres returns aware values so production never hit it, but it made the expiry branch untestable
TC-NAME-001 | Peer resolution | name= resolves one agent in one request | IMPL-065 / #73 | No paging for a known peer | Functional | P1 | Many agents registered | 1) GET /agents?name=<known> | Exactly that agent; one request regardless of registry size | API | yes - test_agents_name_filter.py |  |  |  | Replaces a gate that paged 10x200 rows; a customer copy omitted pagination and silently truncated past 200
TC-NAME-002 | Peer resolution | Match is exact, not substring | IMPL-065 / #73 | Ambiguous resolution is unacceptable | Negative | P1 | Agents 'billing' and 'billing-agent' | 1) GET /agents?name=billing | Returns only 'billing' | API | yes
TC-NAME-003 | Peer resolution | name= applies to both views | IMPL-065 / #73 | logical and epochs both filter | Functional | P2 | Agents registered | 1) GET /agents?name=X&view=logical; 2) same with view=epochs | Both filter correctly (logical_agents.name and agents.name) | API | yes
TC-NAME-004 | Peer resolution | name= does not cross tenants | IMPL-065 / #73 | Filter is ANDed with the org scope | Security | P1 | Same agent name in two orgs | 1) GET /agents?name=X as org A | Only org A's agent | API | yes |  |  |  | Previously indistinguishable, which is why this is pinned
TC-NAME-005 | Peer resolution | Unknown name is empty, not an error | IMPL-065 / #73 | Absence is a valid answer | Negative | P3 | Stack up | 1) GET /agents?name=does-not-exist | 200 with an empty list | API | yes
TC-NAME-006 | Peer resolution | current_did_status is exposed | IMPL-065 / #73 | Callers can refuse a superseded peer | Functional | P1 | Agent with a superseded epoch | 1) GET /agents?view=logical&name=X | current_did_status present and correct | API | yes |  |  |  | Without it, 'refuse a superseded peer' is unimplementable against this endpoint
TC-NAME-007 | Peer resolution | name= cannot resurrect a retired epoch | IMPL-065 / #73 | Filter is ANDed with the superseded exclusion | Security | P2 | Agent with only superseded epochs | 1) GET /agents?name=X&view=epochs | Superseded epochs excluded by default | API | yes |  |  |  | Precisely the stale-DID bug
TC-PLANE-001 | Plane boundary | agent-os does not import the mesh at module scope | #74 | Keep the planes separate | Regression | P2 | Source checkout | 1) Import agent_os; 2) Count agentmesh module-scope imports | Zero (was 49 modules) | Unit test | yes - test_plane_boundary.py
TC-PLANE-002 | Plane boundary | agent-os works without agent-mesh installed | #74 | SDK-only deployments must not need the mesh | Functional | P2 | Environment WITHOUT agent-mesh | 1) Import and use agent_os | Works | CLI | yes
TC-REGR-001 | Regression | Existing agents keep working | all | No break for pre-feature agents | Regression | P1 | DB with pre-feature agents | 1) Browse Agent Registry and Agent Detail; 2) Exercise existing flows | All existing screens and flows work; pre-feature agents show 'not enrolled' | UI + API | partial
TC-REGR-002 | Regression | Backend suite has no new failures | all | Guard against regressions | Regression | P1 | Merged branch | 1) pytest tests/ -q; 2) Diff the FAILING SET against the staging-main baseline, not just the count | Failing set byte-identical to baseline (90 entries: 72 failed + 18 errors) | CLI | n/a |  |  |  | Compare sets, not totals - a count can match while the membership differs
TC-REGR-003 | Regression | SDK suite has no new failures | sdk #20 #21 | Guard against regressions | Regression | P1 | Merged branch | 1) pytest tests/ -q with the correct PYTHONPATH; 2) Diff the failing set | Failing set byte-identical to baseline (25, all environmental) | CLI | n/a |  |  |  | The 25 are environmental: the installed agt-os-kernel predates IMPL-059's PolicyAction vocabulary
TC-REGR-004 | Regression | UI type-checks and builds | ui #28 #29 | Only gate the repo has | Regression | P1 | Merged branch | 1) npx tsc -b; 2) npm run build; 3) npx eslint on changed files | All clean. The ~30 eslint errors elsewhere in src/ are pre-existing | CLI | n/a |  |  |  | This repo has NO test framework - no vitest, no jest, no test files
TC-REGR-005 | Regression | Wheelhouse rebuilt after the SDK release | sdk #21 | Customers get the new SDK | Release | P1 | core #76 merged BEFORE sdk #21 | 1) Rebuild the customer wheelhouse; 2) Install offline; 3) Run an agent through the escrow flow | Same-DID restart works from the wheelhouse build | CLI | none |  |  |  | agt-sdk needs FORK dist names: agt-os-kernel and agt-mesh-platform from core, agt-registry-client from microsoft-source
TC-PERF-001 | Performance | Enrolment endpoint on a large fleet | #78 | Operator screens stay usable | Performance | P3 | Org with 500+ agents and many epochs | 1) Time the enrolment endpoint and /agents/summary | Both respond within the agreed budget | API | none |  |  |  | Summary now loads live Agent rows plus logical ids in Python - worth a look at scale
TC-PERF-002 | Performance | Registry listing with many epochs | IMPL-066 / #73 | Live agents must not fall off the page | Performance | P2 | Agents with many retired epochs | 1) Page the registry | Live agents appear on page 1; retired epochs do not consume the limit | API | yes

## Test-SDK
TC ID | Area | Feature | IMPL / PR | Title | Type | Priority | Preconditions | Steps | Expected Result | Verify Via | Existing Auto Coverage | QA Result | Tested By | Date | Comments
TC-PV-001 | Peer verification | @peer_verified allows a passing peer | IMPL-065 / sdk #20 | Decorated body runs when the peer passes the gate | Functional | P1 | Two agents registered; peer active with trust above the bar | 1) Decorate a delegating function with @peer_verified(peer, min_trust=N); 2) Call it | Body runs; return value unchanged | Unit + agent log | yes - test_decorator_runs_the_body_when_the_peer_passes
TC-PV-002 | Peer verification | @peer_verified refusal prevents the body | IMPL-065 / sdk #20 | A refused peer must not be called at all | Security | P1 | Peer below the bar or inactive | 1) Call the decorated function | Raises AGTPeerUntrusted; the body does NOT execute; no outbound call to the peer | Unit + network capture | yes - test_decorator_refusal_prevents_the_body_from_running |  |  |  | The failure this exists to prevent is a silent ungated peer call. Confirm with a network capture, not just the exception
TC-PV-003 | Peer verification | Exception carries the full verdict | IMPL-065 / sdk #20 | Operators can see why a peer was refused | Functional | P2 | Refused peer | 1) Catch AGTPeerUntrusted; 2) Inspect .verdict | Carries the A2AVerdict with allowed, peer_name, reason and source | Unit | yes - test_exception_carries_the_verdict
TC-PV-004 | Peer verification | Sync functions stay sync | IMPL-065 / sdk #20 | Decorator must not force async on callers | Functional | P2 | Sync delegating function | 1) Decorate a sync function; 2) Call it normally | Runs synchronously; no coroutine returned; refusal still raises before the body | Unit | yes - test_decorator_on_a_sync_function_stays_sync
TC-PV-005 | Peer verification | Signature is not modified | IMPL-065 / sdk #20 | No injected peer argument | Functional | P2 | Decorated function | 1) inspect.signature on the decorated callable | Identical to the undecorated signature - no resolved peer injected | Unit | yes - test_decorator_does_not_change_the_signature |  |  |  | Matches @governed, which never changes a signature. A2A must not be a second idiom
TC-PV-006 | Peer verification | Decorator and kernel.a2a_gate cannot drift | IMPL-065 / sdk #20 | Both surfaces run the same gate | Regression | P1 | Same peer and bar | 1) Evaluate via @peer_verified; 2) Evaluate via await kernel.a2a_gate(peer, min_trust=N); 3) Compare | Identical decision and reason | Unit | yes - test_decorator_and_method_produce_the_same_decision |  |  |  | Two code paths for one policy is how they diverge; this is the pin
TC-PV-007 | Peer verification | Peer is addressed by NAME, not DID | IMPL-065 / sdk #20 | A pinned DID breaks on peer rotation | Functional | P1 | Peer that will rotate its epoch | 1) Gate on the peer NAME; 2) Rotate the peer so it gets a new DID; 3) Gate again | Still resolves and gates correctly after rotation | Integration | partial |  |  |  | DIDs are per-epoch. An initiator that pins a peer DID breaks on that peer's next restart - the stale-DID bug IMPL-065 exists to remove
TC-PV-008 | Peer verification | Unknown peer is refused | IMPL-065 / sdk #20 | Fail-closed on identity | Security | P1 | Peer name not registered | 1) Gate on it | Refused; reason says not registered, not active, or superseded | Unit + agent log | yes - test_refuses_an_unknown_peer
TC-PV-009 | Peer verification | Every inactive status is refused | IMPL-064 IMPL-065 / sdk #20 | revoked, suspended, decommissioned, superseded | Security | P1 | A peer in each of the four states | 1) Gate on each in turn | All four refused | Unit | yes - test_refuses_every_inactive_status |  |  |  | _INACTIVE = revoked, suspended, decommissioned, superseded. Run all four - a regression could drop one
TC-PV-010 | Peer verification | Superseded peer refused END TO END | IMPL-065 / #73 + sdk #20 | The actual goal of IMPL-065 | Security | P1 | Real CP; peer whose epoch was rotated out so did_status=superseded | 1) Resolve the peer by name via the CP; 2) Gate on it; 3) Attempt the delegation | current_did_status=superseded is returned by the CP, the gate refuses, and the handshake is never attempted | Integration - real CP | partial - unit only |  |  |  | This is the pair of CP #73 and SDK #20 working together. Unit tests stub the CP; this case must use a real one
TC-PV-011 | Peer verification | Two status fields are both honoured | IMPL-064 / sdk #20 | status and did_status mean different things | Security | P2 | Peer with status=active but did_status=superseded, and the inverse | 1) Gate on each combination | Refused when EITHER is inactive | Unit | yes |  |  |  | A peer is only usable when neither is inactive. Older CP builds may not expose did_status - confirm the fallback
TC-PV-012 | Peer verification | Peer above the bar is allowed | IMPL-065 / sdk #20 | Trust floor comparison | Functional | P1 | Peer trust >= bar | 1) Gate | Allowed | Unit | yes - test_allows_a_peer_above_the_bar
TC-PV-013 | Peer verification | Peer below the bar is refused | IMPL-065 / sdk #20 | Trust floor comparison | Security | P1 | Peer trust < bar | 1) Gate | Refused with a reason naming the trust and the bar | Unit | yes - test_refuses_a_peer_below_the_bar
TC-PV-014 | Peer verification | Boundary: trust exactly equals the bar | IMPL-065 / sdk #20 | Inclusive comparison | Functional | P2 | Peer trust == bar | 1) Gate | ALLOWED (allowed = trust >= bar) | Unit | partial |  |  |  | Off-by-one worth an explicit case
TC-PV-015 | Peer verification | Attested mode still checks identity | IMPL-065 / sdk #20 | min_trust=0 is not open season | Security | P1 | min_trust=0; peer unknown or inactive | 1) Gate | Refused on IDENTITY despite no trust bar | Unit | yes - test_attested_mode_allows_any_trust_but_still_checks_identity |  |  |  | 0 means attested mode: identity remains fail-closed, only the trust bar is dropped. A common misreading
TC-PV-016 | Peer verification | min_trust precedence | IMPL-065 / sdk #20 | Decorator argument beats the env default | Functional | P2 | AGT_A2A_MIN_TRUST set to X | 1) Decorate with min_trust=Y where Y differs; 2) Gate a peer between X and Y | Y is applied, not X | Unit | partial
TC-PV-017 | Peer verification | An agent never gates against itself | IMPL-065 / sdk #20 | Self-delegation is not a peer call | Functional | P2 | Agent running | 1) Gate on its own name | Not gated / allowed | Unit | yes - test_never_gates_against_itself
TC-PV-018 | Peer verification | Mesh off is allowed and says so | IMPL-065 / sdk #20 | Governance-only deployments still function | Functional | P1 | Mesh wiring absent (no [mesh] extra) | 1) Gate on any peer | Allowed with reason 'mesh off - not gated' and source=mesh_off; a warning is emitted | Unit + agent log | yes - test_mesh_off_allows_and_says_so |  |  |  | Deliberate: there is no trust data to gate on, and refusing every delegation would break governance-only installs. Must be LOUD, not silent
TC-PV-019 | Peer verification | Lookup failure is fail-CLOSED by default | IMPL-065 / sdk #20 | An unreachable CP means no knowledge of the peer | Security | P1 | CP unreachable; a2a_fail_mode default | 1) Gate | Refused; reason names the lookup failure | Unit + agent log | yes - test_lookup_failure_is_fail_closed_by_default |  |  |  | Calling an unverified peer is exactly what this gate exists to stop
TC-PV-020 | Peer verification | fail_mode=open allows on lookup failure | IMPL-065 / sdk #20 | Explicit opt-out is honoured | Functional | P2 | AGT_A2A_FAIL_MODE=open; CP unreachable | 1) Gate | Allowed with a reason naming the fail-open | Unit + agent log | yes - test_fail_mode_open_allows_on_lookup_failure |  |  |  | Contrast with escrow key recovery, which is fail-closed in BOTH modes - see TC-ESC-005
TC-PV-021 | Peer verification | Publish failure does not change the verdict | IMPL-065 / sdk #20 | Fail-open on publication only | Functional | P1 | Trust-edge publish endpoint failing | 1) Gate a passing peer | Verdict remains ALLOWED; publish error is logged, not propagated | Unit | yes - test_publish_failure_does_not_change_the_verdict |  |  |  | A publish error must not turn a trusted peer into a refused one. Note the asymmetry: the DECISION is fail-closed, PUBLICATION is fail-open
TC-PV-022 | Peer verification | One trust edge per peer epoch | IMPL-065 / sdk #20 | No duplicate edge spam | Functional | P2 | Peer gated repeatedly | 1) Gate the same peer many times | One edge published per (peer, did, verdict) | Unit + CP | yes - test_one_edge_per_peer_epoch_but_a_new_one_after_rotation
TC-PV-023 | Peer verification | A new edge after peer rotation | IMPL-065 / sdk #20 | A rotated peer is a new epoch | Functional | P2 | Peer rotates its DID | 1) Gate before and after rotation | A fresh edge is published for the new epoch | Unit + CP | yes
TC-PV-024 | Peer verification | A changed verdict publishes a fresh edge | IMPL-065 / sdk #20 | Refusals must be visible, not just allows | Functional | P1 | Peer allowed once, then its trust decays below the bar | 1) Gate (allowed); 2) Lower the trust; 3) Gate again (refused); 4) Inspect the CP | The refusal IS published | CP | yes - test_a_change_of_verdict_publishes_a_fresh_edge |  |  |  | Real bug this pins: keying on (name, did) alone meant a peer allowed once and later refused never published the refusal, so the CP showed a trusted edge for a peer we had stopped calling
TC-PV-025 | Peer verification | a2a_gate handles peers unknown at import time | IMPL-065 / sdk #20 | Fan-out, capability selection, config-driven names | Functional | P1 | N child agents | 1) await kernel.a2a_gate(name) for each dynamically resolved peer | Each gated independently with correct verdicts | Integration | yes |  |  |  | The escape hatch for cases the decorator cannot express
TC-MESH-001 | Mesh identity | Agent has an Ed25519 DID identity | IMPL-020 / core | Cryptographic identity, not a DB record | Functional | P1 | Agent started once | 1) Inspect the DID and public key | DID = did:mesh:<sha256(public_key) prefix>; Ed25519 key material | Agent log + DB | yes |  |  |  | The DID commits to the key. Do not expect a name-derived DID on the governed path
TC-MESH-002 | Mesh identity | IATP handshake succeeds between two agents | core | A2A trust handshake | Functional | P1 | Two governed agents, both active | 1) Initiate a handshake A to B | Succeeds; a handshake event is recorded | Agent log + CP | partial
TC-MESH-003 | Mesh identity | Handshake against a superseded DID is refused | IMPL-064 / core | The CP refuses retired epochs | Security | P1 | Peer with a superseded epoch | 1) Attempt a handshake against the superseded DID directly | Refused by the CP | API + agent log | yes |  |  |  | Calling a superseded epoch is a guaranteed failure - this is why the gate screens it first
TC-MESH-004 | Mesh identity | Messages are signed | core / design decision | Message signing over mTLS | Security | P2 | Two agents communicating | 1) Capture an A2A message; 2) Verify the signature; 3) Tamper and re-verify | Valid signature verifies; a tampered message is rejected | Capture | partial |  |  |  | Architecture decision: message signing rather than mTLS
TC-MESH-005 | Mesh identity | Capability discovery excludes retired epochs | IMPL-066 / core | A caller must not dial a dead DID | Functional | P2 | Live and superseded epochs both advertising a capability | 1) Search by capability | Only the live epoch is returned | API | yes - test_capability_discovery_excludes_retired
TC-MESH-006 | Mesh identity | Retired peers do not consume the result limit | IMPL-066 / core | Retired rows must not crowd out live ones | Functional | P2 | Many superseded epochs plus one live | 1) Search by capability with a small limit | The live peer is returned | API | yes - test_retired_peers_do_not_crowd_out_discovery
TC-MESH-007 | Mesh registry | Peer resolution is ONE request | IMPL-065 / #73 + sdk #20 | No paging the registry per delegation | Performance | P1 | Registry with 500+ agents | 1) Resolve a known peer by name from the SDK; 2) Count HTTP requests | Exactly one request; independent of registry size | Network capture | partial |  |  |  | Replaces a gate that paged up to 10x200 rows; a customer copy omitted pagination entirely and silently truncated past 200
TC-MESH-008 | Mesh registry | Resolution beyond 200 agents does not truncate | IMPL-065 / #73 | The customer-visible bug | Regression | P1 | Registry with more than 200 agents; target peer ordered beyond 200 | 1) Resolve that peer by name | Resolved correctly | Integration | yes |  |  |  | This is the specific silent-truncation failure the name filter removes
TC-MESH-009 | Mesh registry | Registry cache is used | core §6 resilience | Repeat lookups do not re-hit the CP | Performance | P2 | Mesh registry wired | 1) Resolve the same peer twice in quick succession | Second lookup served from cache | Agent log | partial
TC-MESH-010 | Mesh registry | Breaker opens on repeated CP failure | core §6 resilience | Do not hammer a failing CP | Functional | P2 | CP failing | 1) Drive repeated lookups | Breaker opens; behaviour matches the configured fail mode | Agent log | partial
TC-MESH-011 | Mesh registry | Stale-while-revalidate serves a stale entry | core §6 resilience | Availability during a blip | Functional | P2 | Cached peer; CP briefly unavailable | 1) Resolve during the outage | A stale entry is served and refreshed afterwards | Agent log | partial |  |  |  | Confirm a STALE ALLOW cannot outlive a revocation beyond the agreed window - raise if it can
TC-MESH-012 | Mesh registry | Negative cache for unknown peers | core §6 resilience | Unknown peers do not stampede | Functional | P3 | Unknown peer name | 1) Resolve it repeatedly | Negative result cached for the configured window | Agent log | partial
TC-MESH-013 | Mesh registry | agt-registry-client absent degrades cleanly | sdk #20 | Governance-only mode | Negative | P2 | Mesh wiring active but agt-registry-client NOT installed | 1) Read kernel.mesh_registry; 2) Gate a peer | mesh_registry is None; the gate reports mesh-off rather than crashing | Unit + agent log | yes |  |  |  | Both come from the same [mesh] extra, so this is rare - but it must not crash
TC-MESH-014 | Mesh registry | Cross-org peer is not resolvable | core | Tenant isolation in peer resolution | Security | P1 | Same peer name in two orgs | 1) From an agent in org A, resolve that name | Only org A's peer; org B's is unreachable | Integration | yes
TC-MESH-015 | Mesh registry | Mesh pushes to the CP; the CP does not write back | IMPL-002 / core | Two registries sync, not merge | Functional | P2 | Agent creating a DID | 1) Observe the CP agents table after DID creation; 2) Confirm no reverse write to the trust engine | A lightweight record appears in the CP; no CP-to-trust-engine write | DB + logs | partial |  |  |  | Key design decision - do not re-debate without context
TC-A2A-101 | A2A delegation | Parent delegates to child | core / sdk | Multi-agent topology works | Functional | P1 | Parent and child agents running (e.g. 2 parents x 3 children) | 1) Parent invokes a child through the gate | Delegation succeeds; the edge is recorded in the CP | Agent log + CP | partial |  |  |  | Reference topology: dockerised agents on :9101-:9123 with baseline off
TC-A2A-102 | A2A delegation | AGT_PEER_DID wiring | core / sdk | Documented A2A configuration path | Functional | P2 | Two agents | 1) Configure AGT_PEER_DID per the SDK Agent Developer Guide; 2) Delegate | Works as documented | Agent log | none |  |  |  | Follow the SDK Agent Developer Guide - not editable source installs or direct DB writes
TC-A2A-103 | A2A delegation | Delegation refused when the child is revoked | IMPL-064 / sdk #20 | Kill switch reaches A2A | Security | P1 | Child agent credential revoked | 1) Parent attempts delegation | Refused | Agent log | yes
TC-A2A-104 | A2A delegation | A new DID cannot shed a suspension | IMPL-064 / #77 | Kill inheritance across epochs | Security | P1 | Agent suspended, then it opens a new epoch | 1) Open a new epoch; 2) Attempt delegation | Suspension is inherited; a lifecycle revoked is NOT downgraded to a reactivatable suspended | API + agent log | yes |  |  |  | Carried over from bootstrap consume because it is a property of OPENING AN EPOCH, not of bootstrap
TC-A2A-105 | A2A delegation | One DID cannot be held by two logical agents | IMPL-067 P2 / #77 | Two agents sharing a DID means sharing a private key | Security | P1 | DID already held by a different logical agent | 1) Attempt to attach it to another | 409; never repointed | API | yes
TC-POL-001 | SDK governance | @governed still enforces alongside @peer_verified | IMPL-059 / sdk | The two decorators coexist | Regression | P1 | Agent with policies loaded | 1) Decorate one function @governed and another @peer_verified; 2) Trigger a block on each | AGTBlocked for policy; AGTPeerUntrusted for peer. Neither interferes with the other | Integration | partial
TC-POL-002 | SDK governance | Real CP policies govern the agent | reference / CP | Policy delivery preconditions | Functional | P1 | Policy authored in the CP AND org-bound | 1) Put tool rules in defaults.blocked_actions / require_approval / blocked_patterns; 2) Set AGT_LOCAL_SAFETY_BASELINE=off; 3) Run the agent | Rules are enforced | Agent log + CP decisions | none |  |  |  | The SDK IGNORES rules[] - rules MUST be in defaults.*. Policy must be org-bound. With the local baseline on, results are misleading
TC-POL-003 | SDK governance | Decisions reach the CP | IMPL-004 IMPL-001 | Audit visibility | Functional | P1 | Agent running with audit configured | 1) Trigger allowed and blocked actions; 2) Open Decision Explorer | Decisions appear in the CP | UI + API | partial
TC-POL-004 | SDK governance | Audit delivery never blocks the agent | design decision 6 | Best-effort audit | Functional | P2 | Audit sink unreachable or queue full | 1) Drive many decisions | Agent is never blocked; oldest entries are dropped | Agent log | partial
TC-POL-005 | SDK governance | Policy fetch failure falls back to cache | design decision 5 | Fail-open on remote policy fetch | Functional | P2 | Policy server unreachable; a cached bundle exists | 1) Restart the agent; 2) Trigger a governed action | Last cached bundle is used with a warning; the agent does NOT block all calls | Agent log | partial |  |  |  | Stale enforcement is preferred over broken agents. Contrast with peer verification, which is fail-closed
TC-SDK-001 | SDK packaging | Offline wheelhouse install | reference / sdk | Customers install offline | Release | P1 | Wheelhouse built AFTER core #76 merged | 1) Install the SDK from the wheelhouse with no network; 2) Import agt_sdk | Installs and imports cleanly | CLI | none |  |  |  | agt-sdk needs FORK dist names: agt-os-kernel and agt-mesh-platform from core, agt-registry-client from microsoft-source
TC-SDK-002 | SDK packaging | Escrow works from the wheelhouse build | IMPL-020 P3 + sdk #21 | The edge that CI cannot see | Release | P1 | Wheelhouse installed | 1) Run the escrow flow; 2) Restart the agent | Same DID recovered. Escrow tests must NOT be skipping | CLI + agent log | none |  |  |  | If core #76 is missing, agentmesh.identity.key_backup is absent, escrow tests SKIP rather than fail, and agents mint a new DID per restart while CI looks green
TC-SDK-003 | SDK packaging | run-all.sh brings up the reference agents | reference / sdk | Documented happy path | Smoke | P2 | Wheelhouse installed | 1) Run run-all.sh per the SDK Agent Developer Guide | Agents come up and register | CLI | none
TC-SDK-004 | SDK packaging | API-issued tokens only | reference / sdk | No direct DB writes in test setup | Functional | P1 | QA setting up agents | 1) Obtain every credential through the API / UI | No test procedure writes to the DB or installs from editable source | Process check | n/a |  |  |  | A test that seeds the DB directly can pass while the real flow is broken
TC-SDK-005 | SDK packaging | Correct SDK variant is installed | reference | The 307 gotcha | Regression | P2 | Fresh venv | 1) Confirm which agt_sdk is importable; 2) Run trust operations | No unexpected 307 redirects on trust endpoints | CLI | none |  |  |  | A venv that installs the main SDK where the demo variant is expected causes trust calls to 307. Confirm the import path before blaming the CP
TC-SDK-006 | SDK packaging | Installed package does not shadow the checkout | reference | Test-path hazard | Regression | P1 | Both an installed agentmesh and a checkout present | 1) Run the SDK and agent-mesh suites without PYTHONPATH; 2) Run them with it | Without: modules fail COLLECTION. With: they pass. QA must use the documented PYTHONPATH | CLI | n/a |  |  |  | Silently tests the wrong code otherwise - the failure looks like broken code rather than a mis-pathed test run
TC-SDK-007 | SDK config | Four authentication modes resolve correctly | IMPL-067 P3 / sdk #21 | Credential precedence | Functional | P1 | Each mode configured in turn | 1) AGT_AGENT_TOKEN; 2) AGT_BOOTSTRAP_TOKEN; 3) AGT_CP_TOKEN; 4) none | Each resolves to the documented behaviour; bootstrap wins while set and warns; agent-credential path is preferred | Unit + agent log | yes
TC-SDK-008 | SDK config | diagnostics() reports the runtime state | sdk | Supportability | Functional | P3 | Agent running | 1) Call kernel.diagnostics() | Reports enabled, cp_url, fail_mode, heartbeat, policies_loaded and bootstrap state | Unit | partial
TC-SDK-009 | SDK lifecycle | Heartbeat keeps the agent live | IMPL-066 / sdk | Liveness | Functional | P2 | Agent running with heartbeat on | 1) Let it run past the liveness window | Stays live; the CP does not revoke it | CP + agent log | partial |  |  |  | An IDLE fleet gets epochs revoked - that is expected behaviour, not a bug. See the Environment tab
TC-SDK-010 | SDK lifecycle | Attach happens after bootstrap in the legacy path | IMPL-067 P3 / sdk #21 | Ordering | Regression | P2 | Both bootstrap and agent credential configured | 1) Start the agent | Bootstrap path runs first with a deprecation warning, then identity attach | Agent log | yes